Preparing Sprint 1 .. n in JIRA

SHORT Checklist:

- Define Sprint Goal

MUST be done till Friday

Create Epics

- Create User Stories

- Add Acceptance Criteria

- Estimate Story Points

- Create Sprint in JIRA

- Add Stories to Sprint

Next 2 week

Start Sprint

- Daily standups

- Review + Retrospective

Common Student Team Mistakes

Too many tasks
 No clear sprint goal
 No Definition of Done
 No estimation
 No demo at end

!!!!! Keep first sprint SIMPLE.

1 Define the Sprint Goal (Before JIRA!)

Very important: Sprint ≠ task collection.
You need a clear Sprint Goal.

For example:

- “Device sends temperature data to cloud successfully”

- “First working prototype of sensor data pipeline”

- “Basic firmware reads and transmits sensor values”

!!! Keep it outcome-based, not task-based.

2 Prepare the Product Backlog

In JIRA:

A. Create Epics (big themes)

For smart forest device, typical Epics:

- Firmware development

- Sensor integration

- Communication module (LoRa / LTE / MQTT)

- Backend API

- Database

- Web dashboard

- Power management

- Enclosure design

- Documentation

!!! In JIRA → Create Issue → Select Epic

B. Break Epics into User Stories

Use format:

As a ___
I want ___
So that ___

Example:

- As a system, I want to read temperature from sensor every 10 minutes so that we can monitor forest conditions.

- As a backend system, I want to receive MQTT data so that device information is stored.

- As a user, I want to see temperature history so that I can analyze trends.

In JIRA:

- Create issue type: Story

C. Add Acceptance Criteria

Each story must include:

- Clear “DONE” definition

- Testable conditions

Example:

Acceptance Criteria:

- Sensor returns correct value

- Data transmitted successfully

- No system crash for 1 hour

3 Estimate Stories (Story Points)

Use Fibonacci:

1 – Very small
2
3
5
8
13 – Too big → split it

Student team tip:
If story > 8 → split it.

Use SCRUM Poker, it works online as well https://www.scrumpoker-online.org/en/

In JIRA:

- Open story → Add Story Points

4 Create the Sprint in JIRA

Go to:

Backlog → Create Sprint

Then:

- Name it: Sprint 1 – Device Data Transmission

- Set duration (usually 1–2 weeks for students)

- Drag selected stories into sprint

⚠ Only add stories that help achieve Sprint Goal.

5 Sprint Planning Meeting (Very Important)

During planning:

- Present Sprint Goal

- Review each story

- Discuss:

  - Technical approach

  - Dependencies

  - Risks

- Confirm capacity (how many hours available per team member)

Then:
Click Start Sprint

6 Define Definition of Done (DoD)

Write this clearly in Confluence or shared document:

Example DoD:

- Code pushed to Git

- Code reviewed

- Compiles without errors

- Tested on real hardware

- Documented

- Updated in JIRA

Without DoD, Scrum becomes chaos.

7 During the Sprint

Daily:

- Short standup (15 min)

- What did I do?

- What will I do?

- What blocks me?

In JIRA:

- Move tasks:

  - To Do

  - In Progress

  - Code Review

  - Testing

  - Done

8 End of Sprint

Sprint Review

- Demo working device

- Show real data

- Show dashboard

- Collect feedback

Sprint Retrospective

Discuss:

- What worked?

- What didn’t?

- What to improve?

You can use online tools, like https://www.scrumretro.dev/en/